## Sheet1
Timelines | Backend (Server) | Back Office (Web) | Customers Web App | Customers Mobile App
Week 1 | Initial code setup | Super Admin and Restaurant Admin login UI
DB connectivity and server hosting
Auth module (Super Admin and Restaurant Admin)
| Super Admin Restaurants Listing module | Restaurants Listing UI
Week 2 | Super Admin QR Codes module | QR Generation UI
| Customers App Server DB connectivity and hosting |  | Initial code and routing setup
| Restaurants List module |  | Restaurants Listing
Week 3 Week 4 | Tables listing & merging module | Tables listing & merging UI | Tables listing & merging UI
| Dashboard (Dine-in-orders) module - Admin APIs | Restaurant Menu management UI | Menu Listing
| Dashboard (Dine-in-orders) module - Customer App APIs Phase-1 | Dashboard (Dine-in-orders) UI Phase-1 | Customer menu selection
Week 5 | Dashboard (Dine-in-orders) module - Customer App APIs Phase-2 | Adds-on management UI Dashboard (Dine-in-orders) UI Phase-1 | Adds-on UI
Order placing
Adding more items to order
Week 6 | Restaurant Managers and Staff listing module | Managers and Staff listing UI
| Schedule management module | Schedule management UI
Week 7 | Restaurant Managers and Staff login module | Restaurant Managers and Staff login UI
| Customer Request handling UI | Customer Request handling UI | Call servicing
Check closing
Week 8 | Customers Auth module |  | Customer Login
| Payment module | Payment acceptance UI | Payment implementation
Week 9 Week 10 | Dashboard (Takeaway-orders) module - Admin APIs | Dashboard (Takeaway-orders) UI | Restaurants search
| Dashboard (Takeaway-orders) module - Customer App APIs |  | Takeaway Customer flow
Week 11 | Loyalty management module | Loyalty management UI | Loyalty management UI
| Financial reporting module | Financial reporting UI
Week 12 | In-App Notification module | In-App Notification UI | In-App Notification Integration | In-App Notification Integration
Bugs Fixing